**University planning**

**Week 5 starts: 03-03-2025**

**Week 5-6 (03-03-2025 – 17-03-2025): Research and Analysis / Start of Advice and Design**

* Define the solution.
* Begin designing and writing advise report.
* Reserve 10%-20% in the sprint

**Week 7-8 (17-03-2025 – 31-03-2025): Advice, Design, and Implementation**

* Discuss the solution with the team and gather feedback.
* Start working iteratively on the stories through design and implementation.
* Break down the problem into manageable user stories.
* Reserve 30%-40%

**Week 9-14 (31-03-2025 – 05-05-2025): Analysis, Design, and Development 🡪 midway presentation University.**

* Refining, designing, and developing user stories in iterative sprints.
* Regularly request feedback from the team and adjust where necessary.
* Gather feedback from users.
* Reserve 50%-60%

**Week 15-17 (05-05-2025 - 19-05-2025): Finalization**

* Request feedback from end users.
* Finalize features.
* Write the graduation folder.
* Reserve 50%-60%

**Week 18-20 (19-05-2025 – 02-06-2025): Buffer**

* Address unforeseen challenges and refine the solution.
* Reserve: I do not know yet

Final delivery: **16th of June**